## Assignemnt3.1
RAG Project Status
Task | Description | Status | Notes
Procedural Geometry Setup | Basic scene setup | Done
Object Placement | Random placement of multiple objects | Done
Parametric Generation | Add parameters to control geometry size, shape, and position | Done
Animation Integration | Apply animation to generated objects | Done
Parameter Interconnections | Make parameters interdependent | Done
Scene Composition | Design overall visual aesthetics | Done
Customization UI | Create interface for user customization | Done
Testing | Test procedural generation and animations | Done
Video Demonstration | Record video showing functionality | Done
Submission | Finalize code and documentation | Done
Legend:
Not Started: Task not yet begun
In Progress: Task currently being worked on
In Progress: Task currently being worked on
Completed: Task finished
Date | Description | Status | Changes
DD/MM/Year | A single sentence per event

## Assignment3.2
Task | Description | Status | Notes
Main Idea | Explain basic concept and challenges | Done
Interaction Explanation | Describe user interaction and modification | Done
Group Duties | Define each group member's contributions | Done
Presentation Format | Choose between video or live presentation | Done |  | Video
Submission | Submit video or PowerPoint |  |  | Step | Details | Completed
|  | Overall Status |  | 1. Introduction | Briefly introduce Three.js and its purpose
Legend: |  |  |  |  | Explain the project goals and expected outcomes
Not Started: Task not yet begun |  |  |  | 2. Setup (Environment Preparation) | Explain how to load Three.js (CDN or NPM)
In Progress: Task currently being worked on |  |  |  |  | Describe the basic structure (Scene, Camera, Renderer)
In Progress: Task currently being worked on |  |  |  | 3. Scene Setup | Outline how to create a Scene, Camera, and Renderer
Completed: Task finished |  |  |  |  | Explain camera positioning
Describe how to add the Renderer to the webpage
|  |  |  | 4. Adding Objects | Explain how to add a basic 3D object (e.g., Cube)
Introduce materials and colors for objects
Discuss adding objects to the Scene
|  |  |  | 5. Adding Animation | Introduce requestAnimationFrame() for animations
Explain basic object transformations (rotation, movement)
Describe updating the Renderer in a loop
|  |  |  | 6. Conclusion | Summarize key points covered in the video
Mention additional resources (Three.js documentation)
End with a closing remark

## Assignment3.3 Individual
Criteria | Red (Needs Improvement - 0-2 pts) | Amber (Developing - 3-4 pts) | Green (Excellent - 5 pts) | Status
Model Management | Only one model or hardcoded positions for multiple models | Multiple models placed with some procedural/random distribution | ✅ Multiple models placed with user-controlled distribution and dynamic updates
Interaction | No interaction, models are static | Models can be placed using clicks or basic procedural distribution | ✅ Models interact with the environment, including collision detection and object interaction
Textures & Materials | No textures or basic default materials | Textures included, but no advanced mapping | ✅ Textures, normal maps/bump maps applied for realism
Scene Customization | Fixed size, no customization | Basic scene customization, limited resizing | ✅ Scenario size is fully customizable, dynamically updates
Rendering Quality | Basic rendering, minimal lighting | Improved rendering with lighting adjustments | ✅ Advanced rendering with lighting environment customization
Terrain & Environment | Flat terrain, no dynamic changes | Some terrain variation but not procedural | ✅ Procedural terrain with objects placed above dynamically
Legend:
Not Started: Task not yet begun
In Progress: Task currently being worked on
In Progress: Task currently being worked on
Completed: Task finished
|  |  | Due Date | 27th April
3D 생존 기지 건설 시뮬레이터
날짜 | 작업 내용 | 비고 |  | Status
1일차 (D-14) | - 프로젝트 기획 | 시작 준비 단계
- 핵심 기능 정의
- 개발환경 세팅 (Three.js 등)
2일차 (D-13) | - 기본 지형 생성 | 지형 렌더링 확인
- 카메라 및 조작 컨트롤 구현 (OrbitControls 등)
3일차 (D-12) | - 구조물 오브젝트 임포트/모델링 (간단한 Cube로 시작 가능)
4일차 (D-11) | - 구조물 배치 시스템 구현 (클릭으로 배치 등) | UI 없이 기능 위주 구현
5일차 (D-10) | - 오브젝트 간 충돌 감지 로직 구현 | 겹치기 방지
6일차 (D-9) | - UI 요소 제작 시작 (버튼, 선택창 등)
- 기본 HUD 구성
7일차 (D-8) | - 동적 라이팅, 그림자 처리 | Three.js 기본 조명 활용
- 낮/밤 라이트 테스트
8일차 (D-7) | - 지형 다양화 (언덕, 평지 등) | 선택 사항 (시간 여유 시)
- 간단한 노이즈 지형 생성
9일차 (D-6) | - 자원 시스템 구현 (건물 배치 시 자원 소모 등) | 미니멀 로직 구현
10일차 (D-5) | - UI 개선 | UX 향상
- 구조물 선택 및 삭제 기능 추가
11일차 (D-4) | - 최적화 (렌더링, 메모리 관리 등) | 성능 개선 단계
- 코드 리팩토링
12일차 (D-3) | - 테스트 및 디버깅 | 직접 플레이 테스트
- 버그 수정
13일차 (D-2) | - 최종 점검 | 피드백 받을 수 있으면 좋아요
- 사용자 흐름 테스트
14일차 (D-1) | - 배포 준비 (GitHub Pages 등) | 포트폴리오용 정리
- 결과 정리 (시연 영상 등)
|  |  | Due Date | 27th April

## Assignment Group Projects
Group 26 :
Criteria | Red (Needs Improvement - 0-2 pts) | Amber (Developing - 3-4 pts) | Green (Excellent - 5 pts) | Status
Project Selection & Planning | No application selected or unclear design | Application selected, but planning needs refinement | ✅ Clear design and plan with roles assigned for each group member
Development Progress | No significant progress or no core functionality developed | Core functionality is developed but lacking some features | ✅ Full development of required features, including interactive elements
Individual Contribution | One or two group members contribute, others inactive | Group members contribute, but unevenly or with limited involvement | ✅ All group members contribute equally, with clear individual roles
Presentation Quality | Unclear presentation, not well-rehearsed, over 10 minutes | Presentation rehearsed but some issues with timing or clarity | ✅ Clear, well-rehearsed, concise presentation within 10 minutes
Technical Difficulty & User Experience | Basic application with no advanced features | Application includes some advanced features, but limited user experience focus | ✅ High technical difficulty with a well-designed user experience and smooth interactions
Final Code Submission | Incomplete code or no submission | Code submitted but may lack functionality or documentation | ✅ Fully working code with proper documentation and all team members contributing
Overall
Legend:
Not Started: Task not yet begun
In Progress: Task currently being worked on
In Progress: Task currently being worked on
Completed: Task finished
|  |  | Due Date (Presentation) | 16th May
Gantt Chart | Gantt Chart'!A1 |  | Due Date (Submission) | 30th May
Git-hub | salieri009/ThreeJSUTS26
Branch Manual | Git-Branching Guidance'!A1
Phase | Task | Start Date | End Date | Duration | Task Status
1. Project Setup | Create GitHub repository and structure | 2025-03-28 | 2025-03-29 | 2
| Install dependencies and configure tools | 2025-03-28 | 2025-03-29 | 2
| Set up basic Three.js scene | 2025-03-30 | 2025-03-31 | 2
2. Planning | Define project scope and functionality | 2025-04-01 | 2025-04-02 | 2
| Break down tasks and assign responsibilities | 2025-04-01 | 2025-04-02 | 2
3. Modeling | Design and create 3D models (e.g., objects, environment) | 2025-04-03 | 2025-04-10 | 8
| Apply textures and optimize models | 2025-04-11 | 2025-04-13 | 3
4. Core Features | Implement camera controls | 2025-04-14 | 2025-04-15 | 2
| Add lighting (ambient, directional) | 2025-04-16 | 2025-04-17 | 2
| Enable object placement and interaction | 2025-04-18 | 2025-04-21 | 4
5. Integration | Integrate models into the scene | 2025-04-22 | 2025-04-24 | 3
| Add UI elements (buttons, menus) | 2025-04-25 | 2025-04-27 | 3
6. Testing & Debugging | Test functionality and fix bugs | 2025-04-28 | 2025-05-02 | 5
| Optimize performance | 2025-05-03 | 2025-05-05 | 3
7. Deployment | Prepare final build | 2025-05-06 | 2025-05-07 | 2
| Deploy to GitHub Pages | 2025-05-08 | 2025-05-08 | 1

## Git-Branching Guidance
Category | Details | Branch Name | Purpose | Priority
Main Branch (main) | Holds stable, deployable code with completed features ready for production. | main | Holds stable, deployable code for the interactive farm project.
Development Branch (dev) | The central branch for ongoing work. Team members merge feature branches here after review. | dev | The central integration branch where all features are merged for testing before finalizing in main.
Feature Branches | Individual branches for specific tasks, e.g., feature/terrain-generation, feature/camera-controls. | feature/terrain-system | Handles terrain generation (grass, soil, elevation) for a realistic farm environment. | ?
Pull Requests (PR) | Merging feature branches into dev via PRs for code review and team discussion. | feature/farm-objects | Adds interactive farm objects like barns, houses, fences, and other visuals.
Conflict Management | Regularly pull from dev into feature branches to update and resolve conflicts early. | feature/plant-system | Implements planting, growing, and harvesting of crops.
Testing | Features are tested in dev before merging into main to ensure stability and functionality. | feature/animal-system | Manages animal interactions, including movement, behaviors, and sounds.
Issue Tracking | Use GitHub Issues to track tasks, bugs, and discussions for better team collaboration. | feature/user-controls | Develops user interaction, like camera movement, clicking, dragging, or hovering over objects.
Demo Deployment | Deploy project previews via GitHub Pages for live demonstrations of progress. | feature/ui-elements | Implements UI components like menus, inventory systems, and notifications.
|  | feature/environmental-effects | Adds weather effects (rain, sunlight, wind) to enhance the farm environment.
|  | feature/sound-system | Integrates sound effects for animals, tools, and environmental sounds like rain or wind.
|  | feature/multiplayer | (Optional) Implements multiplayer functionality for collaborative farm management.
|  | feature/deploy-system | Prepares deployment scripts for hosting the farm project on platforms like GitHub Pages.